## Dashboard
AI Calling System Testing Dashboard
Metric | Count |  | Quick Test URLs
Total Tests | 37 |  | Health | https://inbound-test.ladderaiagent.com/api/health
Passed | 13 |  | Inbound Stats | https://inbound-test.ladderaiagent.com/api/inbound/stats
Failed | 7 |  | Inbound Calls | https://inbound-test.ladderaiagent.com/api/inbound/calls
Blocked | 0 |  | Dashboard | https://inbound-test.ladderaiagent.com
In Progress | 0 |  | Inbound Number | +918065480098
Not Started | 17
Pass % | 35.14%
Go-Live Rule: Do not merge to main/live until all High priority tests are Passed and no crash appears in Coolify logs.
Category | Total | Passed
AI Prompt | 1 | 0
Appointments | 1 | 0
Basic App Health | 2 | 2
CRM | 6 | 3
Call Logs | 1 | 1
Campaigns | 2 | 0
Go Live | 1 | 0
Inbound | 11 | 3
Logs | 2 | 0
Outbound | 2 | 1
Recordings | 2 | 1
Regression | 2 | 0
Stability | 2 | 0
Stats | 2 | 2

## Testing Checklist
ID | Category | Test Case | Steps | Expected Result | Priority | Status | Tester | Test Date | Notes / Issue | Evidence Link
T01 | Basic App Health | API health check | Open /api/health in browser. | status ok; required services configured. | High | Passed | karuna | 2026-05-11
T02 | Basic App Health | Dashboard login/logout | Open dashboard, login, logout, try wrong password. | Login works; wrong password rejected; logout returns to login. | High | Passed | karuna | 2026-05-11
T03 | Stats | Live Config badges | Open Stats tab and review all config badges. | LiveKit, Google API, Supabase, outbound trunk, Gemini, S3/R2 show configured. | High | Passed | karuna | 2026-05-11
T04 | Stats | Dashboard charts and counters | Check total calls, booked count, call chart, average duration chart. | Stats load without errors and reflect calls. | Medium | Passed | karuna | 2026-05-11
T05 | Outbound | Single call test | Single Call tab: call your mobile with business/service details. | Phone rings; AI speaks; log and recording saved. | High | Passed | karuna | 2026-05-11
T06 | Outbound | Batch call test | Batch Call tab: test 2-3 numbers. | Batch starts; each number processed safely; no duplicate crash. | High | Failed | karuna | 2026-05-11 | I have uploaded 2 number , call went both number same time, voice agen responsd to first number but there is a delay in responding , but 2nd number no answer, log:- [2026-05-11T15:00:36.874090] warning/server: CRM contact upsert skipped 'NoneType' object has no attribute 'data' [2026-05-11T15:00:05.058454] info/agent: Gemini native-audio: model will greet autonomously from system prompt [2026-05-11T15:00:04.726170] info/agent: Recording started: egress=EG_HNADrkdFAPo3 [2026-05-11T15:00:01.745403] info/agent: Agent session started [2026-05-11T14:59:59.151557] info/agent: Call ANSWERED — +919150151775 picked up, starting AI session now [2026-05-11T14:59:44.335897] info/server: Call dispatched to +918143554346 room=call-918143554346-4518 [2026-05-11T14:59:43.929069] info/agent: Dialing +919150151775 via SIP trunk ST_eM4ttK2yVPo3 [2026-05-11T14:59:43.675077] info/agent: Connected to LiveKit room: call-919150151775-7169 [2026-05-11T14:59:38.810892] info/server: Call dispatched to +919150151775 room=call-919150151775-7169
T07 | Campaigns | Campaign creation and start | Create test campaign with 2 numbers, start it. | Campaign created and calls begin; statuses update. | High | Failed | karuna | 2026-05-11
T08 | Campaigns | Campaign stop/pause safety | Pause/stop campaign while running if feature exists. | Campaign stops safely; no extra unexpected calls. | Medium | Failed | karuna | 2026-05-11 | when pasuse ans resume ca, call reppeted
T09 | CRM | Manual lead add | CRM tab: add one lead with name, phone, city, source. | Lead appears in CRM list and search. | High | Failed | karuna | 2026-05-11
T10 | CRM | Upload leads CSV/Excel | Upload 3 test leads with phone/name/city/source/budget. | Upload succeeds; invalid/duplicate phones handled safely. | High | Failed | karuna | 2026-05-11
T11 | CRM | CRM filters | Filter by source, city, business name, campaign, CRM status, outcome, due today. | Only matching leads show. | Medium | Passed | karuna | 2026-05-11
T12 | CRM | Download filtered leads | Click Download Filtered Leads Excel and CSV. | Files download and contain only filtered leads. | Medium | Passed | karuna | 2026-05-11
T13 | CRM | Call selected leads | Select 1-2 leads and click Start Calling Selected Leads. | Only selected leads are called; call log linked. | High | Not Started
T14 | CRM | Status manager | Add/delete test status; mark selected as Hot Lead / Not Interested. | Status saves; dropdown and lead update correctly. | Medium | Passed | karuna | 2026-05-11
T15 | AI Prompt | Default/custom prompt save | Open AI Prompt tab; save short custom prompt; test a call. | Prompt saves and call behavior reflects it. | Medium | Not Started
T16 | Appointments | Outbound appointment booking | During outbound call say: I want appointment tomorrow at 5 PM. | Appointment saved with correct date/time and phone. | High | Failed | karuna | 2026-05-11
T17 | Call Logs | Call logs and export | Open Call Logs; download /api/export/calls.xlsx and CSV. | Logs visible; Call Type column exists; exports open. | High | Passed | karuna | 2026-05-11
T18 | Recordings | Recording storage status | Open recording storage/retention or /api/recordings/storage. | Storage usage and recording count load. | Medium | Passed | karuna | 2026-05-11
T19 | Recordings | Recording playback/link | Check inbound and outbound recording links after calls. | Recording link works; metadata saved. | High | Failed | karuna | 2026-05-11
T20 | Inbound | Inbound health badges | Inbound tab: check all health badges. | Enabled, trunk, dispatch rule, phone, agent profile, business, transfer are green. | High | Passed
T21 | Inbound | Inbound settings save | Set INBOUND_ENABLED, phone, trunk, dispatch rule, agent, business, greeting; save. | Settings save; health updates without error. | High | Passed
T22 | Inbound | Basic inbound call answer | Call +918065480098 and say: I want service details. | AI answers with inbound greeting and responds. | High | Passed
T23 | Inbound | Inbound CRM existing contact | Call from a number already in CRM. | CRM contact loaded; no duplicate lead created. | High | Not Started
T24 | Inbound | Inbound CRM new contact | Call from a new number. | CRM creates Unknown Caller with source inbound_call and status New. | High | Not Started
T25 | Inbound | Inbound appointment booking | During inbound call say: I want appointment tomorrow 6 PM. | Appointment saved; call outcome updated. | High | Not Started
T26 | Inbound | Inbound callback request | Say: Please call me back tomorrow morning. | Callback/follow-up note saved; outcome callback_requested. | Medium | Not Started
T27 | Inbound | Inbound human transfer | Say: I want to talk to a human. | Transfer attempted to DEFAULT_TRANSFER_NUMBER; transferred_to and reason saved. | High | Not Started
T28 | Inbound | Inbound FAQ answer | Add FAQ text; call and ask pricing/service question. | AI answers from FAQ; no outbound wording. | Medium | Not Started
T29 | Inbound | Inbound calls table | Inbound tab → Refresh Inbound Calls. | New inbound call appears with room, caller, outcome, duration, recording. | High | Not Started
T30 | Inbound | Inbound stats update | Open /api/inbound/stats after test calls. | total_inbound_calls and other counters update. | Medium | Not Started
T31 | Logs | Inbound logs validation | During inbound call, check Logs/Coolify logs. | Shows received job, inbound-agent, room inbound-, caller detected, starting AI session. | High | Not Started
T32 | Logs | No crash errors | Review logs after inbound/outbound calls. | No job crashed, AttributeError, 8081 address already in use, or API key errors. | High | Not Started
T33 | Stability | Restart test app | Restart inbound test app in Coolify. | App starts; FastAPI healthy; workers on 8081 and 8082. | High | Not Started
T34 | Stability | Redeploy test app | Redeploy inbound test app. | Deployment finishes; dashboard/login/workers still work. | High | Not Started
T35 | Regression | Outbound after inbound | After inbound testing, place outbound single call again. | Outbound /api/call still works normally. | High | Not Started
T36 | Regression | Inbound after outbound | After outbound test, call inbound number again. | Inbound still answers; no worker conflict. | High | Not Started
T37 | Go Live | Final go-live readiness | Check all High priority tests are Passed. | Ready to merge only if all critical tests pass. | High | Not Started

## Settings
Status Options
Not Started
In Progress
Passed
Failed
Blocked
Retest
Priority Options
High
Medium
Low